## README
CONDITION SURVEY — captured in the field
Department of Feeder Roads. Hand this file to the Master Estimator on the desktop.
Road name | Osubeng Jn - Osubeng
Road code | ER-KWS-009
Region | Eastern Region
District | Kwahu South
Surveyed by | Dr. Ampadu
Date of survey | 2026-08-05
Road length (m) | 8000
Stretches | 6
Point items | 3
HOW TO LOAD THIS
1 | Open this file and the Master Estimator side by side.
2 | For each of A_Corridor, B_Drainage, C_Pavement and D_Points: select the data block from row 5 down, copy, and paste into the same sheet of the estimator at row 5.
3 | Do the same for E_Rules (rows 5-9) and for the Value column of F_Road_Data.
4 | Type the road name, code, region and district on 00_Project. The road length is measured for you.
5 | Read 90_Checks. Every test must say OK before the bill is issued.
Chainages are in METRES.
This file records what was seen. It is not an estimate and carries no rates.

## A_Corridor
FORM A — CORRIDOR, CLEARING AND EARTHWORKS
From | To | Township Y/N | Vegetation | Raise road: fill (cm) | Cut to widen (cm) | Cut width L+R (m) | Fill to widen (cm) | Fill width L+R (m) | Notes
0 | 1200 |  | GB
1200 | 1800 |  | GB |  | 120 | 4
1800 | 4400 |  | GB
4400 | 5000 |  | LB |  |  |  | 60 | 4
5000 | 8000 |  | LB

## B_Drainage
FORM B — DRAINAGE
From | To | Ditch L | Ditch R | U-drain L (cm) | U-drain R (cm) | Trap. drain L | Trap. drain R | Kerb L | Kerb R | Scour checks | Scour spacing (m) | Ret. wall L | Ret. wall R | Notes
0 | 7000 | RE | RE
7000 | 8000 |  |  | 60 | 60

## C_Pavement
FORM C — PAVEMENT AND SURFACING
From | To | Surface condition | Treatment (override) | Sub-base cm (ovr) | Base cm (ovr) | Prime (ovr) | Seal 1 (ovr) | Seal 2 (ovr) | Notes
0 | 8000 | P | [5 empty] | N

## D_Points
FORM D — POINT ITEMS
Chainage | Type | Family | Cells | Size | Length (m) | Orientation | Quantity | Notes
500 | PR_CULVERT | PC | 2 | 900 | 10 | Skew
1500 | PR_CULVERT | PC | 3 | 1200 | 12 | Right Angle
5000 | PR_CULVERT | BC | 2 | 3x3 | 12 | Right Angle

## E_Rules
FORM E — TREATMENT RULES
Condition | What it looks like | Treatment | Sub-base (cm) | Base (cm) | Primer seal | First seal | Second seal
G | Good — shape and camber sound, light maintenance only | BLADE
F | Fair — camber lost in places, some potholing | RESHAPE | 10 | 15 | Y | Y | Y
P | Poor — badly deformed, potholed, camber gone | RESHAPE | 15 | 15 | Y | Y | Y
VP | Very poor — impassable in rain, gravel lost | SCARIFY | 15 | 15 | Y | Y | Y
NR | No road — new alignment or total reconstruction | SCARIFY | 15 | 20 | Y | Y | Y

## F_Road_Data
FORM F — ROAD DATA
Values copied into 00_Project. A ! marks a template figure not yet confirmed for this road.
Confirm? | Parameter | Value | Unit | Note | Name
CROSS-SECTION
| Carriageway width | 7 | m |  | P_CW
| Shoulder width (one side) | 1 | m | Formation width = CW + 2×SW, computed | P_SW
| Existing carriageway width | 4 | m |  | P_ExtCW
| Width for primer seal | 8 | m |  | P_PrimeW
| Width of sealing | 7 | m |  | P_SealW
PAVEMENT
| Sub-base thickness | 0.15 | m | E_Rules sets it per stretch in cm | P_SubbaseT
| Base thickness | 0.15 | m |  | P_BaseT
! | Overhaul distance, sub-base | 6 | km | Borrow pit to site, less the 1 km free haul | P_OH_Sub
! | Overhaul distance, base | 9 | km | Quarry to site, less the 1 km free haul | P_OH_Base
SURFACING DESIGN RATES
| Primer seal binder rate | 1.4 | l/m² |  | P_PrimeRate
| First seal binder rate | 1.3 | l/m² |  | P_Seal1Rate
| Second seal binder rate | 1.2 | l/m² |  | P_Seal2Rate
| Binder fraction of primer | 0.84 | - | Balance is cutter oil | P_BinderPct
| Cutter-oil fraction of primer | 0.16 | - | Binder + cutter must come to 1.00 | P_CutterPct
| 10 mm chipping coverage | 120 | m²/m³ |  | P_Chip10
| 14 mm chipping coverage | 100 | m²/m³ |  | P_Chip14
HAULAGE DISTANCES
! | Sand (fine aggregate) | 15 | km |  | P_HaulSand
! | Coarse aggregate | 25 | km |  | P_HaulCoarse
! | Chippings | 60 | km |  | P_HaulChip
! | Fill material | 2 | km |  | P_HaulFill
AGGREGATE YIELD FACTORS
! | Fine agg. per m³ lean concrete | 0.58 | m³/m³ | C10/40 | P_FineLean
! | Coarse agg. per m³ lean concrete | 0.92 | m³/m³ | C10/40 | P_CoarseLean
! | Fine agg. per m³ structural conc. | 0.55 | m³/m³ | C20/20 – C30/20 | P_FineStr
! | Coarse agg. per m³ struct. conc. | 0.88 | m³/m³ | C20/20 – C30/20 | P_CoarseStr
ROAD FURNITURE
! | Traffic signs per km (each type) | 2 | nr/km | Three types are billed, so this is ×3 | P_SignsPerKm
! | STOP line per km | 5 | m/km |  | P_StopPerKm
! | Speed ramps per km | 0.25 | nr/km |  | P_RampsPerKm
! | Lane separation line factor | 0.6 | m/m | of sealed length | P_LaneLineF
! | Centre line factor | 0.4 | m/m |  | P_CentreLnF
! | Edge line factor | 2 | m/m | both edges | P_EdgeLnF
! | Pedestrian crossing factor | 2 | m/km |  | P_PedXF